## CLASS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6
Likelihood |  |  |  | Incredible | Improbable | Remote | Occasional | Probable | Frequent | Classification
Category | Rating | 1 | Negligible | 1 | 2 | 3 | 4 | 5 | 6 | N/ACC
frequent | 6 | 2 | Marginal | 2 | 4 | 6 | 8 | 10 | 12 | RFI
probable | 5 | 3 | Critical | 3 | 6 | 9 | 12 | 15 | 18 | ACC
occasional | 4 | 4 | Catastrophic | 4 | 8 | 12 | 16 | 20 | 24
remote | 3
improbable | 2
incredible | 1
Severity
Category | Rating
catastrophic | 4
critical | 3
marginal | 2
negligible | 1
Risk = Severity x Likelihood
Risk | Category
0… 6 | Acceptable (ACC)
7… 12 | Requires Further Investigation (RFI)
13… 24 | Not acceptable (N/ACC)

## RISK
Risk ID | Potential Risk | Cause ID | Potential Causes | Severity | Likelihood | Risk | Mitigation ID | Mitigation
R1.1 | Missed deadline | C1.1.1 | Illness | 1 | 2 | 2 | M1.1.1 | If ill, report special circumstances in advance.
|  | C1.1.2 | Not sure the theme | 2 | 1 | 2 | M1.1.2 | Meet with supervisor early to determine the research theme.
|  | C1.1.3 | Poor time management | 3 | 4 | 12 | M1.1.3 | Make the Gantt plan properly.
|  | C1.1.4 | Unfinished project | 5 | 3 | 15 | M1.1.4 | Submit weekly work report and report to supervisor.
R1.2 | Feature creep | C.1.2.1 | Over-ambitious project spec | 3 | 2 | 6 | M1.2.1 | Discuss project plan with supervisor to create necessary and worthwhile goals.
R1.3 | Error Model design | C1.3.1 | Complexity of the Error Model | 4 | 3 | 12 | M1.3.1 | Avoid overdesigning the model and design flexible error recovery strategies
|  | C1.3.2 | Poor Test Coverage | 3 | 2 | 6 | M1.3.2 | Increase test coverage related to data, model inference, and prediction processes, and ensure proper monitoring and logging.
R1.4 | Loss of data | C1.4.1 | Poor version control | 5 | 3 | 15 | M1.4.1 | Implement two different version control strategies at the start of the project and regularly check the project versions.
R1.5 | Risk of model overfitting | C1.5.1 | Dataset Too Small | 2 | 3 | 6 | M1.5.1 | Perform data augmentation on the dataset.
|  | C1.5.2 | Insufficient Data Augmentation | 3 | 3 | 9 | M1.5.2 | Increase the diversity of data augmentation strategies and adjust the intensity of augmentation.
|  | C1.5.3 | Neglecting the Performance on the Test Set | 4 | 2 | 8 | M1.5.3 | Use different evaluation metrics, cross-validation, and set up a monitoring metric for early stopping during training.
R1.6 | Insufficient detection accuracy | C1.6.1 | Unbanlanced Dataset | 3 | 2 | 6 | M1.6.1 | Perform data augmentation to balance class distribution.
|  | C1.6.2 | Improper model training parameters | 4 | 3 | 12 | M1.6.2 | Tune the model hyperparameters, using an appropriate learning rate and loss function.
R1.7 | Model inference is slow | C1.7.1 | High model complexity | 1 | 4 | 4 | M1.7.1 | Optimize the model structure, reduce the number of parameters and apply image downsampling
|  | C1.7.2 | Insufficient Hardware performance | 2 | 3 | 6 | M1.7.2 | Test the model on high-performance hardware.
R1.8 | Data quality problem | C1.8.1 | Low resolution of satellite images, cloud occlusion or noise | 2 | 4 | 8 | M1.8.1 | Apply data preprocessing and combine other remote sensing data sources to improve data quality.
R1.9 | Schedule delay | C1.9.1 | Excessive time spent in the model optimization and evaluation phase | 4 | 4 | 16 | M1.9.1 | Create a detailed timeline, prioritize completing core features before optimization.
R2.1 | Project results do not meet expectations | C2.1.1 | Performance metrics are not met | 3 | 3 | 9 | M2.1.1 | Conduct multiple rounds of testing and evaluation in the mid and final stages of the projec.