## Semester 1
Week No. & Date | Planned Objectives | Tasks Undertaken/Achieved | Uncompleted Tasks | Supervision Meeting Summary | Important Information / Resources
Week 1 - October 21st 2024 to October 27th 2024 | Literature review | Literature review | Literature review | 1. Read the proposal at least three or four times before submitting it, checking the format, font and font size of the proposal, as well as the diagram, and do not paste the equation in the image format 2. For citations, use appropriate tools such as Endnote or Mandalay 3. For equations, use the appropriate tool, such as mathtype 4. In addition, there should be no Chinese language in any form in the proposal 5. For charts/block diagrams, use appropriate tools such as Ms Visio 6. Don't copy images from other sources, but you must draw from Scratch and then use it in your own work. 7. Listen carefully to JoJo 8. Use academic words in your proposal, but not everyday English words 9. For data sets, try to add some samples, such as data set pictures to attract your work, and try to add visual effects, such as block diagrams, etc | 1.https://link.springer.com/article/10.1007/s11676-020-01230-7 2.https://onlinelibrary.wiley.com/doi/full/10.1155/2022/8044390?msockid=3c4380bc0bb169543205959e0a9f68bb 3.https://www.sciencedirect.com/science/article/abs/pii/S1568494623003800
| Project proposal | Project proposal | Project proposal |  | Section 3-4 is completed
| DataSet collection | DataSet collection | DataSet collection |  | Datasets was downloaded from NASA FIRMS (the Fire Information for the Resource Management System), links are as follows: https://firms.modaps.eosdis.nasa.gov/
| DataSet classification |  | DataSet classification |  | Not yet started
Week 2 - October 28th 2024 to November 3rd 2024 | Literature review | Literature review | No | It is best to review more than 20 articles related to forest fire detection. | This paper reviews the literature about this project in the last five years, summarizes the advantages and disadvantages of its methods, and compares the performance of several models in tabular form.
| Comparison of existing models | Comparison of existing models |  | Compare as many schemes as possible in order to find the current model with the best performance in detecting forest wildfires. | After comparison, I found that most forest fire detection models are integrated or optimized on the YOLO algorithm, because it ensures lightweight detection while implementing detection.
| Project proposal | Project proposal |  | 1. Try to add this picture-type equation to your model proposal 2. Add pictures of the proposed architecture to make the proposal look attractive and impressive | Have completed the Project proposal，Ethic form, AI declaration, Plagiarism Report
| Database selection and download | Database selection and download |  | 1. Database: 42,850 images, with 22,710 images belonging to the Wildfire. https://github.com/doguilmak/Wildfire-Prediction-from-Satellite-Imagery https://www.kaggle.com/datasets/abdelghaniaaba/wildfire-prediction-dataset 2. Other wildfires data website: https://firms.modaps.eosdis.nasa.gov/active_fire/ https://oxai.github.io/wildfire/datasets/ https://paperswithcode.com/dataset/burned-area-delineation-from-satellite | I ended up choosing this dataset: 42,850 images, with 22,710 images belonging to the Wildfire. https://github.com/doguilmak/Wildfire-Prediction-from-Satellite-Imagery https://www.kaggle.com/datasets/abdelghaniaaba/wildfire-prediction-dataset, 70% of the data set is used as the training set, 15% as the test set, and the remaining 15% as the verification set.
Week 3 - November 4rd 2024 to November 10rd 2024 | Data preprocessing | Data preprocessing | Data preprocessing | 1.Perfect the proposal
| Data set partition | Data set partition | Data set partition |  | Not yet started
| Build the model | Build the model | Build the model |  | Not yet started
Week 4 - November 11st 2024 to November 17th 2024 | Data preprocessing | Data preprocessing | Data preprocessing | 1. What is the image? The image is a matrix. 2. Why do you choose YOLOv5 instead of the most advanced YoloV11? Because YOLOv11 is unstable, YOLOv5's experience in forest fire detection is more worthy of reference. 3. What if the number of images is too low/unbalanced? Image preprocessing: enhancement, transformation, etc. 4. How do you determine which part is fire? Consider the sub-Mask technique. 5. What is the difference between machine learning and deep reading learning? Machine learning includes a variety of algorithms, and deep learning is more image oriented.
| Data set partition | Data set partition | Data set partition |  | Not yet started
| Build the model | Build the model | Build the model |  | Not yet started
Week 5 - November 18th 2024 to November 24th 2024 | Data preprocessing | Data preprocessing | Data preprocessing
| Data set partition | Data set partition | Data set partition
| Build the model | Build the model | Build the model
Week 6 - November 25th 2024 to December 1th 2024 | Data set partition | Data set partition | Data set partition
| Data preprocessing | Data preprocessing | Data preprocessing
Week 7 - December 2nd 2024 to December 8th 2024 | Data set partition | Data set partition | Data set partition
| Data preprocessing | Data preprocessing | Data preprocessing
| Progress proposal | Progress proposal | Progress proposal
Week 8 - December 9th 2024 to December 15th 2024 | Data set partition | Data set partition | Data set partition
| Data preprocessing | Data preprocessing | Data preprocessing
| Progress proposal | Progress proposal | Progress proposal
Week 9 - December 16th 2024 to December 22rd 2024 | Data set partition | Data set partition | Progress proposal
| Progress proposal | Progress proposal
Week 10 - December 23th 2024 to December 29rd 2024 | Build the model | Build the model | Build the model
| Progress proposal | Progress proposal